## Columns
Order | Column name | Work state it represents | WIP limit | WIP based on (headcount) | Exit criteria (when a card may move on)
1 | Backlog | Prioritized, not started | none | n/a | Top item is detailed enough to start
2 | In Progress | Actively being worked | 4 | 3 people plus one | Work is finished and ready to hand off
3 | Ready for Review | Done, waiting for reviewer | 3 | exposes handoff wait | A reviewer pulls it
4 | In Review | Being reviewed | 2 | 2 reviewers | Approved or sent back with notes
5 | Done | Shipped or published | none | n/a | Nothing; archive after one week

## Swimlanes
Swimlane | Dimension (team, priority, client) | Marker (label or section) | Special rule
Expedite | priority | Red Expedite label | Only one item at a time, ever
Campaign work | workstream | Blue label | Planned, deadline-driven
Always-on work | workstream | Grey label | Recurring, follows the same columns